## Notes
Items that need to be investigated and included in deployment instructions:
If we change the drive letter for the NAS, we need to change logging on all SQL Agent jobs and maintenance plans.
any other implications of change Nas drive letter (ie celtrak_data_last_weekend restore, etc)?
Need to configuration Quorum and decide voting parties.
Rafael is looking into dynamic quorum using Windows Server 2012 R2 Standard.
Dynamic quorum means that Windows removes a vote if the server is unavilable. Therefore Cluster stays up.
Will test later by shutting down servers.
Once Live, we will need additional System Monitor alerts:
Ping Cluster IP address (all other SQL alert should be dependant on this one - ie if the cluster does no SQL servers will work).
If the number of quorom votes decreases (ie should be 5) then alert.
Ping all servier involved (ie bert, bert1, ernie, ernie1, etc)
If a failover occurs, system monitor alert should fire (ie check if there is any change in the primary).

## Deployment Steps
TimeLine | Task | Deployment Phase
21 Days before Deployment | Purchase 4 licenses (8 cores) for SQL Server 2014 Enterprise without Software Assurance. Save to \\backoffice\Applications\SoftwareRepository\SQLServer | 1
7 days before Deployment | Re-Config existing Unit 4 SAN and rebuild Ernie Server: | 1
1) Break mirroring between Bert & Ernie
2) Suspend Mirroring System Monitor Alert
3) Destory Ernie server
4) Implement SAN changes (Refer to "SAN & IT Settings" tab).
6 days before Deployment | Create new Ernie server with Windows 2012 R2 Standard OS. | 1
Verify server settings (Refer to OS Server Settings tab).
5 days before Deployment | Create Windows Failover Cluster (Refer to Cluster Settings) | 1
5 days before Deployment | Perform SQL Server 2014 Enterprise installation. (Refer to "SQL Installation FCI" tab). | 1
5 days before Deployment | Create additional Temp DB files (Refer to Temp DB Files tab) | 1
5 days before Deployment | Restore each database backup, differential and transaction log files to Ernie in NoRecovery state. (Refer to Restore Backups tab) | 1
5 days before Deployment | After installation of SQL Server, review SQL Server settings and add all non-database specific settings. (Refer to SQL Server settings tab). | 1
5 days before Deployment | Implement Log Shipping. (Refer to Log Shipping tab). | 1
Days of Deployment | Carry out various deployment steps. (Refer to Deployment Phase 1 tab). | 1
2 days after Deployment | Destroy and Rebuild Bert | 2
1) Implement SAN changes (Refer to "SAN & IT Settings" tab).
3 days after Deployment | Create new Bert server with Windows 2012 R2 Standard OS. | 2
Verify server settings (Refer to OS Server Settings tab).
3 days after Deployment | Perform SQL Server 2014 Enterprise installation. (Refer to " SQL Installation FCI" tab (replace Ernie with Bert in instructions). | 2
5 days before Deployment | Create additional Temp DB files (Refer to Temp DB Files tab) | 2
5 days before Deployment | Restore each database backup, differential and transaction log files to Ernie in NoRecovery state. (Refer to Restore Backups tab) | 1
4 days after Deployment | After installation of SQL Server, review SQL Server settings and add all non-database specific settings. (Refer to SQL Server settings tab). | 2
5 days after Deployment | Configure Availability Groups between Ernie and new Bert (Refer to Availability Groups tab) | 2
5 days after Deployment | Set Ernie as a ReadOnly server (Refer to "Set Ernie to ReadOnly" tab) | 2
7 days after Deployment | Carry out various deployment (create listener and failver) steps. (Refer to Deployment Phase 2 tab). | 2
14 days after Deployment | Add a new node to FCI in unit 9 & unit 4 (Refer to New Node to FCI tab).

## SAN & IT Settings
Step | Category | Task | Comment
1 | LUNs | Destroy existing LUNs | Destroy existing SQL server LUNs so that they can be re-created.
2 | LUNs | Re-create LUNs | Create the following LUNs:
DB System (S) - 50GB
DB Data (D) - 1.4TB
DB Log (L) - 400GB
DB Archive (F) - 1.9TB
DB ArchiveLog (G) - 200GB
DB Temp (T) - 50GB
NAS_Backup2 (N) - 3.3TB
3 | Formatting | Ensure 64k cluster | Verify that Windows OS and SAN are formatted with 64k clusters. In VM server: => CMD => DISKPART (wait for it to finish) => List volume => Note the volumne numbers for SQL disks (probably (3-8) => type "SELECT VOLUME 3" => type "FILESYSTEMS" => Verify that under Current File allocations, that Allocation Unit Size = 64K. => Repeat for each SQL volume.
4 | SAN provisioning | Each LUN to be eagerzeroedthick (Thick Provision Eager Zeroed). | Each VMDK should be eagerzeroedthick (Thick Provision Eager Zeroed). To confirm this: => VMWare vSphere Client (192.168.51.37 - U9 & 192.168.51.53 - U4) => Find your VM machine, right click & Edit Settings => For each of the 6 SQL Hard Disks, check Disk Provisioning Type is "Thick Provision Eager Zeroed". (The 1st hard disk, used for operating system, will be Thin Provisioned).
5 | Virtaul Adapter | Each LUN should have it's own Paravirtual SCSI (PVSCSI) adapter. | Each VMDK should have it's own Paravirtual SCSI (PVSCSI) adapter. To confirm this: => VMWare vSphere Client => Find your VM machine, right click & Edit Settings => SCSI controller 1, and under SCSI BUS Sharing - "Virtual" should be selected. (Note: Eoghan has chosen "LGI Logic SAS & Virtual" instead of "VMware Paravirtual & Virtual" as there are notes online saying that Paravirtual is not supported where there is a SQL Cluster).
6 | LUNs | LUN boundry & partition alignment | Eoghan to confirm that VMDK's have 1M boundry and that partition are in alignment (should happen by default in Windows 2008 and above).
7 | VM resources | Memory | Consious that memory is thin provisions on VMWare, RAM for Bert/Ernie should be fully reserved so that VMWare cannot balloon into Bert/Ernie. To confirm this: => VMWare vSphere Client => Find your VM machine, right click & Edit Settings => Resources tab => For Memory, you should see "Reservatio" amount set to 32000MB or the following should be ticked "Reserve all guest memory (all locked)".
8 | VM resources | CPU | Consious that CPU is thin provisions on VMWare, CPU for Bert/Ernie should be fully reserved so that VMWare cannot balloon into Bert/Ernie. Especially important now that Bert/Ernie is reduced from 8 to 4 cores. To confirm this: => VMWare vSphere Client => Find your VM machine, right click & Edit Settings => Resources tab => For CPU, you should see "Reservatio" amount set to 4000MH (ie 4 cores).
9 | iSCSI Config | Verify iSCSi Config | Verify iSCSi Config. iSCSi config to be different to previus setup. Eoghan to decide on optimal iSCSi config.
10 | Static IP config | Confirm Static | Eoghan to confirm that all SQL servers (Bert, Ernie, Cluster, listener, etc) have static IP and not assigned by DHCP.
11 | Disk Format | Disk Formatting | => Run MCC => File => Add/Remove Snap-in… => Disk Management => For each disk, ensure them have the drive letter (change if necessary) => If not able to change drive letter in disk management, use CMD: => diskpart, list volume, select vol X, assign letter=D => In necessary, bring the disks online => Right click each disk, format, and ensure the are NTFS and Default (we already verified in previous step that they are 64k).

## OS Server Settings
Step | Category | Task | Comment | To be completed by
1 | Server Settings | Operating System: Clock should be set to GMT/UTC | Clock/change data and time settings/change time zone…/untick "automatically adjust clock for Daylight Saving time" & Clock/change data and time settings/untick "notify me when clock changes" & apply | DBA
2 | Server Settings | Operating System: Power Saving Mode | Set Power Saving mode on Operating System to "High Performance". Control panel/power options/ high performance. | DBA
3 | Server Settings | Operating System: Automatic Updates | Should be disabled. Control Panel\All Control Panel Items\Windows Update\Change settings\Never check for updates (not recommended) & untick "give me recommended updated the same way I receive important updates" | DBA
4 | Server Settings | Operating System: Anti-Virus | Should be disabled. Verify that there is none. Confirm with Eoghan. | IT
5 | Server Settings | Operating System: Trusted Installer | Should be disabled. Confirm this with IT team. Confirm with Eoghan. | IT
6 | Server Componant | .NET Framework 3.5 | Install .NET Framework 3.5: | DBA
=> Navigate to Server Manager
=> click Manage and then select Add Roles and Features
=> Installation type screen, select Role-based or feature-based installation
=> Select the target server.
=> In Select features screen, tick .Net Framework 3.5 Features.
=> Install.
7 | NAS | Setup | Map NAS drive on Ernie as drive letter N. It should have same folder structure as before. | IT

## Cluster Settings
Cluster Settings
Taks | Comments
Enable Cluster Features on the server | => Navigate to Server Manager
=> click Manage and then select Add Roles and Features
=> Installation type screen, select Role-based or feature-based installation
=> Select the target server.
=> In Select features screen, tick "Failover Clustering".
=> Add features and Install. (If already done then Eoghan must have already installed this).
Create a Windows Cluster | => Open Failover Cluster Management
First check if Eoghan has already created the cluster:
=> Right click on "failover Cluster Manager" in the panel on left: "Connect to Cluster…". Look for "sqlcluster.celtrak.local".
=> If you find this Cluster, check in Node to see if Ernie is there.
If the Cluster does not exist, create it:
=> Right click on "failover Cluster Manager" in the panel on left:
=> Type "Ernie" as server name => Next, "Yes, When I click Next, Run con…" => Run all tests (recommended) (results should all be successful or not applicable). => For step "Access Point for Administering the Cluster", under address input the IP address given by Eoghan for the Cluster and Cluster Name = SQLCLUSTER
=> Confirm and create new cluster
=> Ignore the warning re quorum witness, we will do this later.
Check Disk | In SQLCLUSTER/Storage/Disks Add 6 disks if they are not there. Right click Disk, Add Disk & select 6 disks.
5th Quorum | Now that Cluster is created, ask Eoghan to add 5th quorum vote to Cluster. This should be in Unit 9 but not be on VMWare or SAN. To verfiy, connect to SQLCLUSTER in Failover Cluster Manager, click on SQLCLUSTER amd under Cluster Core Resources you will be see File Share Witness.

## SQL Installation FCI
Step | Category | Task | Comment
1 | Mapped/Mounted Drives | Mapped/Mounted Drives | Ensure that the following drives are monted and the correct folders created:
=> (DB Data) D:\sqlserver_data
=> (DB Data) D:\sqlserver_data\OLAP
=> (DB Archive) F:\sqlserver_data
=> (DB ArchiveLog) G:\sqlserver_log
=> (DB Log) L:\sqlserver_log
=> (DB Log) L:\sqlserver_log\OLAP
=> (DB System) S:\sqlserver_system
=> (DB Temp) T:\tempDB
=> (DB Temp) T:\tempDB\OLAP
=> (NAS_Backup) N:\sqlserver\various
2 | Cluster Node | Add the Ernie server as a Node of the cluster | => Connect to the cluster created in the steps before (Open Failover Cluster Management, right click Failover Cluster Manager and Connect to SQLCLUSTER)
=> In the 'Nodes' tab, Check if Ernie is added to Cluster. If not, right click, add node, type 'Ernie' (Just in case you haven't added this server to the Cluster yet - Follow steps in Cluster Setting tab). Extra steps for Bert Only: => When adding the node to the cluster, untick "Add all eligible storage to the cluster" during setup. => Once node is added, go to Failover Cluster Manager. => Right click Disks & Add disks. Select the 6 disks. => Right click Disks again => Move Available Storage => Select Node... => Bert In disks, you should now have 6 disks with Ernie as owner and 6 with Bert as owner (refer to screen shot)..
3 | Installation | Install a new Instance | Run "setup.exe" from SQL Server 2014 Enterprise installation media in \\backoffice\Applications\SoftwareRepository\SQLServer\"XXXXX"
In "SQL Server Installation Media Center" go to "Installation" and select "New SQL Server Failover Cluster…"
SQL Server 2014 Setup:
=> Product Key:
=> License Terms: Accept
When you see the following warning:
=> Go to Control Panel\Network and Sharing Center, Change adapter Settings, hit ALT on keyboard, Advanced Tab, advanced settings, change the connections order, setting LAN before Heartbeat (or Cluster Network).
Re-Run SQL installation "Install Failover Cluster Rules".
=> Setup Role: SQL Server Feature Installation
=> Feature Selection: Select all except:
=> Data quality Client
=> Documentation Components
=> Master data services
If in the next steps you face the following error:
=> Open Failover Cluster Manager, go to Storage\Disks, you will see the column "Assigned To" Cluster Shared Volume
=> If you can see Disks: Select all disks you are going to use, right click, "Remove from Cluster Shared Volume". Assigned To value should now be "Available Storage".
=> If there are no disks there already, Add disks (6). Confirm that Assigned To value should now be "Available Storage".
SQLFCIU4
Re-run SQL Server validation
=> Instance Configuration
=>SQL Server Network Name: SQLFCIU4 (or SQLFCIU9 for BERT) (You do need to specify the network name) If you are told this instance name is already in use, talk to Eoghan about removing AD/DNS records for previous SQL Server instances.
=> Instance ID: Do not use the default. This is because both the Unit 9 and Unit 4 FCI SQL installations cannot use the default instance ID. If we use default in Unit 4, we will need to use named instance ID in unit 9. This combination will work fine. But if we are not going to use default Instance ID in unit 4, we might as well not use default in unit 9 either (to be consistant). Input instance ID as SQLU4 (or SQLU9 for BERT).
=> Instance Name: Not sure if we need to. Let's set it as SQLU4 (or SQLU9 for BERT).
=> Cluster Resource Group
Change Name of SQL Server Cluster resource group name = "SQL SERVER (UNIT4) RG" (or "SQL SERVER (UNIT4) RG" for BERT).
Ignore warnings => Available Storage (The cluster group "Available Storage is reserve…" => Cluster Group (The cluster group "Cluster group" is reserve…"
=> Cluster Disk Selection:
=> Select all 6 disks and Next
=> Cluster Network Configuration
=> Select the tick box for IPv4 => Under Address input the IP address of the Failover instance Unit 4 (or unit 9 for Bert) (provided by Eoghan) (NOT the IP address of the Cluster or Ernie).
=> Server Configuration:
=> Set all services to manual except SQL Server Browser = Automatic.
=> For each service (except Browser & Full-text), change account name to CELTRAK\administrator & put in e* password. Ensure to change any service that is not greyed out.
=> Collation tab: SQL_Latin1_General_CP1_CI_AS
=> Database Engine Configuration
=> Server Configuration
=> Add Current User
=> Select Mixed Mode and enter 3x.. password.
=> Data Directories
=> Data Root directory: S:\sqlserver_system
=> User database: D:\sqlserver_data
=> User database log: L:\sqlserver_log
=> Temp DB: T:\TempDB
=> Temp DB Log: T:\TempDB
=> Backup: N:\sqlserver\backup
Analysis Services Configuration:
=> Server Configuration
=> Multidimensional
=> Add Current User
=> Data directories:
=> Data directory: D:\sqlserver_data\OLAP
=> Log File Directory: L:\sqlserver_log\OLAP
=> Temp Directory: T:\TempDB\OLAP
=> Backup: N:\sqlserver\backup
Reporting Services Native Mode: Install and configure
Distributed Replay Controller: Add Current User
Distributed Replay Client:
=> Controller Name: Ernie_CONTROLLER
=> No change to directories
INSTALL
4 | Installation | Stop services | In "SQL SERVER CONFIGURATON MANAGER", stop any SQL Server Service that are running (ie Analysis/Reporting services) that is not SQL Server (MSSQLSERVER).
5 | Installation | Service Packs | Check if there are any service packs to install. At the time of installation, there was only 1 service pack but it is faulty (Micrsoft pulled it). http://sqlserverbuilds.blogspot.ie/ http://www.brentozar.com/archive/2015/04/breaking-news-dont-install-sql-server-2014-sp1/ | DO NOT INSTALL
6 | Installation | Verification | Verfiy SQL Server edition: SELECT @@VERSION
7 | Installation | Move System Databases | Please refer to tab "Temp DB Files".

## Temp DB Files
/*
/*MOVING SYSTEM DATABASE FILES IS NO LONGER REQUIRED*/
/*SELECT dbid,name,filename FROM sys.sysaltfiles*/
/*
The following directories should have already been created:
=> D:\sqlserver_data
=> D:\sqlserver_data\OLAP
=> F:\sqlserver_data
=> G:\sqlserver_log
=> L:\sqlserver_log
=> L:\sqlserver_log\OLAP
=> S:\sqlserver_system
=> T:\TempDB
=> T:\TempDB\OLAP
*/
/*
############################################
Move msdb, model and master
############################################
*/
SELECT name, physical_name
FROM sys.master_files
WHERE database_id IN (DB_ID('msdb'), DB_ID('model'), DB_ID('master'))
ALTER DATABASE msdb MODIFY FILE ( NAME = MSDBData, FILENAME = 'S:\sqlserver_system\MSDBData.mdf')
ALTER DATABASE msdb MODIFY FILE ( NAME = MSDBLog, FILENAME = 'S:\sqlserver_system\MSDBLog.ldf')
ALTER DATABASE model MODIFY FILE ( NAME = modeldev, FILENAME = 'S:\sqlserver_system\model.mdf')
ALTER DATABASE model MODIFY FILE ( NAME = modellog, FILENAME = 'S:\sqlserver_system\modellog.ldf')
/*
Open "SQL Server Configuration Manager"
Stop SQL Server (MSSQLSERVER) service
Move MSDBData/model/ MASTER mdf & ldf Files to the new location
(from location C:\Program Files\Microsoft SQL Server\MSSQL12.MSSQLSERVER\MSSQL\DATA
to S:\sqlserver_system)
Navigate to "SQL SERVER CONFIGURATON MANAGER".
Go into the properties of "SQL Server (MSSQLSERVER)" in SQL Server Services.
Startup Parameters tab:
Replace
-dC:\Program Files\Microsoft SQL Server\MSSQL.1\MSSQL\DATA\master.mdf;
-eC:\Program Files\Microsoft SQL Server\MSSQL.1\MSSQL\LOG\ERRORLOG;
=-lC:\Program Files\Microsoft SQL Server\MSSQL.1\MSSQL\DATA\mastlog.ldf
with
-dS:\sqlserver_system\master.mdf;
-eS:\sqlserver_system\Log\ERRORLOG;
=-lS:\sqlserver_system\mastlog.ldf
Apply
Rename the old files, ie. Old_master.mdf, just to be sure that the instance is using the new directory
Start SQL Server (MSSQLSERVER) service
If SQL Server starts without problems, STOP it again
*/
/*
############################################
Move MSSQLSYSTEMRESOURCE
############################################
*/
/*
NET START MSSQLSERVER /f /T3608
In CMD, type CD C:\Program Files\Microsoft SQL Server\Client SDK\ODBC\110\Tools\Binn
In CMD, type SQLCMD -S. -E
In CMD, type (one at a time)
ALTER DATABASE mssqlsystemresource
MODIFY FILE (NAME=data, FILENAME= 'S:\sqlserver_system\mssqlsystemresource.mdf');
GO
ALTER DATABASE mssqlsystemresource
MODIFY FILE (NAME=log, FILENAME= 'S:\sqlserver_system\mssqlsystemresource.ldf');
GO
NET STOP MSSQLSERVER
cmd Move the Files from C:\Program Files\Microsoft SQL Server\MSSQL12.MSSQLSERVER\MSSQL\Binn
to S:\sqlserver_system.
cmd NET START MSSQLSERVER /f /T3608
In CMD, type CD C:\Program Files\Microsoft SQL Server\Client SDK\ODBC\110\Tools\Binn
In CMD, type SQLCMD -S. -E
ALTER DATABASE mssqlsystemresource set Read_only;
GO
Open a new CMD window:
cmd NET STOP MSSQLSERVER
Start SQL Server (MSSQLSERVER) service in "SQL Server Configuration Manager"
####################################################################
Open Management Studio (SSMS)
####################################################################
*/
SELECT name, physical_name AS CurrentLocation, state_desc
FROM sys.master_files
/*
############################################
SQL Agent
############################################
*/
/*
Start SQL Server Agent.
Right click on the sql agent "Error Logs" node, select configure and change the Error log dir to S:\sqlserver_system\log\SQLAGENT.OUT
OK
SQL Server Configuration Manager/SQL Server Services/properties of SQL Server Agent (MSSQLSERVER).
Advanced/Dump Directory
Change from
C:\Program Files\Microsoft SQL Server\MSSQL12.MSSQLSERVER\MSSQL\LOG\
to
S:\sqlserver_system\log\
Apply
*/
*/
/*
############################################
Temp DB files
############################################
*/
SELECT name, physical_name
FROM sys.master_files
WHERE database_id = DB_ID(N'tempdb');
USE MASTER
GO
ALTER DATABASE [tempdb] ADD FILE ( NAME = N'tempdev1', FILENAME = N'T:\tempDB\tempdev1.mdf' , SIZE = 1500MB , FILEGROWTH = 10%)
GO
ALTER DATABASE [tempdb] ADD FILE ( NAME = N'tempdev2', FILENAME = N'T:\tempDB\tempdev2.mdf' , SIZE = 1500MB , FILEGROWTH = 10%)
GO
ALTER DATABASE [tempdb] ADD FILE ( NAME = N'tempdev3', FILENAME = N'T:\tempDB\tempdev3.mdf' , SIZE = 1500MB , FILEGROWTH = 10%)
GO
ALTER DATABASE [tempdb] MODIFY FILE ( NAME = N'tempdev', SIZE = 1500MB , FILEGROWTH = 10%)
GO
/*
Restart SQL Server using SQL Server configuration Managera
*/

## Restore Backups
no | Task
1 | For each database execute the following script on Bert: EXEC master.dbo.sp_GenerateRestoreScripts @ps_DBname = DATABASENAME , @ps_new_mdf_location = 'D:\sqlserver_data' --Input correct location (change for archive) , @ps_new_ldf_location = 'L:\sqlserver_log' --Input correct location (change for archive) , @pl_with_recovery = 0 Note: You need will be alter this sproc to allow it to work on SQL Server 2014 edition.
If this stored procedure doesn't exist you can find it in Trunk.
Paste the results from the "messages" tab into Ernie.
Before executing, do a find and replace all "G:\" with "\\bert\G$\"
Execute code on Ernie.
2 | NB: Make a note of the name of the last transaction log file that you restored. You may need this later. | celtrak_paul_2_trn1
3 | Repeat for each database

## SQL Server settings
Step | Location 1 | Location 2 | Task
1 | Server Properties | Memory | Set Maximum server Memory (MB) to 26000.
2 | Server Properties | Processors | Boost SQL Server priority should not be ticked.
3 | Server Properties | Security | Tick "Cross database ownership chaining".
4 | Security | Logins | => Exec master.dbo.sp_help_revlogin on Bert. If this stored procedure doesn't existing create it using "U:\SQL Database Team\Projects\SQL Server 2014 Enterprise Upgrade\Deployment\logins_migration.sql" => In results, replace "BERT" with "SQLFCIU4" => In results, remove login "NT AUTHORITY\SYSTEM", "CELTRAK\Administrator" and 3 "BERT\SQLServer2005..." as they already exists in SQLFCIU4 => Paste results into Ernie and execute.
5 | Management | Database Mail | Configure Database Mail (see below how)
6 | SQL Agent | Operators | Script each SQL Server Agent / Operator and manually verify that they match Bert.
7 | SQL Agent | Jobs | Script each enabled SQL Agent job on BERT and combine into 1 script. => Ensure to change locations of NAS drive (ie replace G:\ to N:\) => Disable each job in the script before executing on Ernie (@enabled=0 under sp_add_job).
8 | SQL Agent | Alerts | Script each SQL Server Alerts. => NB after executing on Ernie, look at the properties of the new Alerts and ensure in Response section that "Notify Operators" is ticked and select "DBA Team".
9 | SQL Service Properties | Enable AlwaysOn AG: | Open SQL Server Configuration Manager, SQL Server Services, right click SQL Server (MSSQLSERVER), properties, AlwaysOn High Availability, in Windows failover cluster name - select the cluster, then tick box on "Enable AlwaysOn Availability Groups". Restart SQL Server.
10 | SQL Server Network Config | TCP/IP protocol | Enable TCP/IP protocol in SQL config manager. Should be done already. In Server Configuration Manager, navigate to => SQL Server Network Configuration > Protocols for MSSQL Server, right-click TCP/IP, and click Enable
11 | RegEdit | Change Regedit setting: NtfsDisable8dot3NameCreation | NTFS can generate both short and long name. Value of 1: NTFS does not create short file names. Although this setting increases file performance, applications that cannot process long file names, and computers that use different code pages, might not be able to find the files. Run regedit.exe HKEY_Local_Machine\SYSTEM\CurrentControlSet\Control\FileSystem Change value of NtfsDisable8dot3NameCreation from 2 to 1.
12 | RegEdit | Change Regedit setting: LargeSystemCache | Specifies whether the system maintains a standard size or a large size file system cache, and influences how often the system writes changed pages to disk. Value of 0: Establishes a standard size file-system cache of approximately 8 MB. The system allows changed pages to remain in physical memory until the number of available pages drops to approximately 1,000. This setting is recommended for servers running applications that do their own memory caching, such as Microsoft SQL Server, and for applications that perform best with ample memory, such as Internet Information Services (IIS). Run regedit.exe HKEY_Local_Machine\SYSTEM\CurrentControlSet\Control\Session Manager\Memory Management Change value of LargeSystemCache from 1 to 0.
13 | RegEdit | Change Regedit setting: DisablePagingExecutive | Specifies whether user-mode and kernel-mode drivers and kernel-mode system code can be paged to disk when not in use. Value of 1: Drivers and the kernel must remain in physical memory. Run regedit.exe HKEY_Local_Machine\SYSTEM\CurrentControlSet\Control\Session Manager\Memory Management Change value of DisablePagingExecutive from 0 to 1.
14 | SecPol | Instant File Initialization | This should already be enabled anyway. Verify that it is. => Run secpol.msc => Security Settings\ Local Policies. => User Rights Assignment => Perform volume maintenance tasks => Double click and Add User or Group.. => Add SQL Server Service account (ie celtrak\administrator).
RESTART SQL SERVER
Linked Servers:
In Server Objects/Linked Server/Providers, SQL 2005 has more providers.
This shouldn’t be an issue and we don't have linked servers anyway.
It is good to be aware of it anyway, just in case.
In case the following two linked server providers are required (SQLXMLOLEDB, SQLXMLOLEDB.4.0), below is the link to download them:
https://www.microsoft.com/en-us/search/Results.aspx?q=sqlxml&form=DLC
Configure Database Mail
=> In Managerement, right click Database Mail, "configure database mail"
=> Select "Set up Database Mail by performing the following tasks"
=> If prompted to ask you to enable Database Mail feature, select Yes.
=> Type "SQLServerTeam" in profile name
=> Configure SMTP account as follow:
For Public Profile, tick the box and change Default Profile = Yes.
no change required to Private Profile.
Next & Finish

## Log Shipping
Log Shipping is a process to automatically restore transaction logs (trn) files to another server.
Important items to note.
1) Because we are using different editions of SQL server, the secondary databases must be left in Restoring state (ie NORECOVERY).
2) It is possible to perform Log Shipping from older SQL edition to new SQL edition. But it is not possible to perform Log Shipping from newer SQL edition to an older SQL edition.
Step | Category | Task | Comment
1 | Firewall Access | Open the port 5022 | In both servers: => Run "Windows Firewall with Advanced Security" => Right click "Inbound Rules" and New Rule... => Port => TCP and Specific Local ports: 5022 => Allow the connection => Untick "public" => Name = SQL Server Availability Groups
2 | Firewall Access | Open the port 1433 | In both servers: => Run "Windows Firewall with Advanced Security" => Right click "Inbound Rules" and New Rule... => Port => TCP and Specific Local ports: 1433 => Allow the connection => Untick "public" => Name = SQL Server Port
3 | Restore | Restore all databases | Ensure you have restored each database to Ernie as per instructions in "Restore Backups" tab.
4 | Maintenace Plan | Stop Maintenance Plan | Stop (modify maintenance plan and disable each step) each Maintenance Plan (full backup, differential and transaction) for the restored database (Ernie).
5 | Restore | Transactional | Restore any new transaction log (trn) files generated since you did the restore (you should have previously noted the last trn file restored).
6 | Log Shipping | Setup | Remote into Bert server and open SSMS.
Go into properties of chosen database & Transaction Log Shipping.
Tick "Enable this as a primary database in a log shipping configuration".
Backup Setting:
=> Network Path = \\bert\G$\sqlserver\transaction_logs_log_shipping
=> Local Path = G:\sqlserver\transaction_logs_log_shipping
=> Delete Files older than: 7 days
=> Alerts is no backup occurs within: 1 hours
=> Job name: LSBackup_database_name
=> Leave schedule as every 15 mins
Secondary Database:
=> Add..
=> Connect to SQLFCIU4 and select database
=> Initialize Secondary Database tab: select "No, The Secondary Database is initialized".
=> Copy Files tab: Select an appropriate folder on Ernie (preferables NAS, if NAS not available D drive). Put in full location (ie \\Ernie\D$\...) => Delete copied files after: 7 Days => Leave schedule as every 15 mins
=> Restore Transaction Log tab: Select "no recovery mode". => Delay restoring backups at least: 0 mins => Alert if no restored occurs within: 45 mins => Leave schedule as every 15 mins
Use Bert as monitoring server instance (leave all settings as default).
7 | Log Shipping | Extra Setup | Update ALL SQL Agent jobs for Log Shipping on both Bert and Ernie to notify DBA team if job fails. 4 SQL Agent jobs per database (2 on Bert and 2 on Ernie).
8 | Log Shipping | Verify | NB: For each database verify that the transaction log files are being restored to Ernie. In Ernie, view the history of SQL Agent job LSRestore_database_name for each database. Expand details of jobs and ensure that files are being restored.

## Deployment Phases
Deployment Phases
Phase 1:
Name | VM Machine Name | SQL Server Name | IP Address | Comment
SQLCLUSTER | NA | NA | Spare IP Address 1
ERNIE server | ERNIE | N/A | Spare IP Address 2
Failover instance Unit 4 (FCI U4) | N/A | ERNIE | 192.168.51.40 (bert original) | Moved IP Address
Phase 2:
Name | VM Machine Name | SQL Server Name | IP Address | Comment
SQLCLUSTER | NA | NA | Spare IP Address 1
ERNIE server | ERNIE | N/A | Spare IP Address 2
Failover instance Unit 4 (FCI U4) | N/A | ERNIE | Spare IP Address 3 | Move IP Address
BERT server | BERT | N/A | Spare IP Address 4
Failover instance Unit 9 (FCI U9) | N/A | BERT | Spare IP Address 5
LISTENER | NA | NA | 192.168.51.40 (bert original) | Moved IP Address
Phase 3:
Name | VM Machine Name | SQL Server Name | IP Address | Comment
SQLCLUSTER | NA | NA | Spare IP Address 1
ERNIE server | ERNIE | N/A | Spare IP Address 2
Failover instance Unit 4 (FCI U4) | N/A | ERNIE | Spare IP Address 3 | Move IP Address
BERT server | BERT | N/A | Spare IP Address 4
Failover instance Unit 9 (FCI U9) | N/A | BERT | Spare IP Address 5
LISTENER | NA | NA | 192.168.51.40 (bert original) | Moved IP Address
ERNIE2 server | ERNIE2 | N/A | Spare IP Address 6
BERT2 server | BERT2 | N/A | Spare IP Address 7

## Deployment Phase 1
Step | Task | Comment
1 | Stop and disable all SQL Server Agent Jobs on Bert, except those related to the log shiping
2 | Turn off (shut down) all applications consoles: => Waldorf => Fozzy => GoSafe => MOTA => System Monitor
3 | Log Shipping: => Disable all Log shipping SQL Agent jobs on Bert and Ernie. => Generate last transaction log: for each database manually execute SQL Agent job "LSBackup_database_name" on Bert. => Ensure that all transaction logs files have been shipped to Ernie. Manually start Ernie SQL Agent job "LSCopy_BERT_database_name". (This is always at least one behind so I expect to need to do this). => On Ernie, manually run "LSRestore_BERT_database_name" to restore all remaining transaction log files. Using history of SQL Agent job, verify that all transaction log fiels were restored.
4 | Remove Log Shipping: => On Bert, go to properties of each database. In transaction log shipping, untick. This should delete SQL Agent jobs.
5 | Take Ernie databases out of recovering state. => RESTORE DATABASE database_name WITH RECOVERY
6a | Run a SQL script to verify last restored file for each database (U:\SQL Database Team\Projects\SQL Server 2014 Enterprise Upgrade\Deployment):
=> Check Latest restored file.sql
6b | Verify that databases are synchronized (U:\SQL Database Team\Projects\SQL Server 2014 Enterprise Upgrade\Deployment):
=> Verify tables are in-sync.sql (execute on both Bert and Ernie)
7 | Turn off SQL Agent on Bert.
8 | For each database on Ernie.
| => DBCC UPDATEUSAGE ('database name') | How long will this take to run? Ignore as takes to long.
9 | For each database on Ernie.
| => USE [database name] GO DBCC CHECKDB WITH DATA_PURITY | How long will this take to run? Ignore as takes to long.
10 | Refresh all views: Execute U:\SQL Database Team\Projects\SQL Server 2014 Enterprise Upgrade\Deployment\Refresh all user views.sql. (Master.dbo.spt_value view will give an error when you refreh, ignore it).
11 | Re-IP the Bert server with another IP address.
12 | Re-IP the Ernie server with IP address "192.168.51.40".
13 | Turn on SQL Agent and enable jobs on Ernie (SQLFCIU4/SQLU4).
14 | Before switching on applications, restart Ernie server (entire server - not just SQL).
15 | Turn on Waldorf application consoles except JBOSS_GPRS
=> Check that application is working. Ask application owner to verify no errors on console. => If it is, turn on JBOSS_GPRS and verify new tk_mu_data records on celtrak_data.
16 | Turn on Fozzy, GoSafe, MOTA, System Monitor applications.
=> Check that applications are working. Ask application owner to verify no errors on console.
17 | Manually re-create all 6 maintenance plans in Bert on SQLFCIU4. => Ensure to change location of NAS drive. => Ensure to disable all maintenance plans jobs on SQLFCIU4
18 | Use Maintenance Plans to generate a full backup on SQLFCIU4 for all database except celtrak_data_archive (do not delete old backup files from Bert).
19 | After full backup files have been generated, enable Maintenance Jobs (excluding archive).
20 | Use Maintenance Plans to generate a full backup on SQLFCIU4 for celtrak_data_archive (do not delete old backup files from Bert).
21 | After full backup files have been generated, enable archive Maintenance Jobs.

## Deployment Phase 2
Step | Task | Comment
1 | Stop and disable all SQL Server Agent Jobs on Ernie.
2 | Turn off (shut down) all applications consoles: => Waldorf => Fozzy => GoSafe => MOTA => System Monitor
3 | Failover from Ernie to Bert: => On Bert, in Mgt Studio, right click on SQL_Server_AG (in Availability Groups) => Failover...
4 | Ask Eoghan to re-IP Ernie to another IP address.
5 | Create Listener: => On Bert, in Mgt Studio, right click on SQL_Server_AG (in Availability Groups) => Add Listener… => Listener DNS Name = SQL_Server_AG_L => Port = 1433 => Network Mode = Static IP => Add => Input BERT IP address (192.168.51.40). Ensure subnet is correct.
6 | Verify that databases are synchronized (U:\SQL Database Team\Projects\SQL Server 2014 Enterprise Upgrade\Deployment). Ernie should be a readable secondary:
=> Verify tables are in-sync.sql (execute on both Bert and Ernie)
7 | Add another vote to quorum (TBD - file share, corless machine, etc)
8 | Although it shouldn't be required, use the opportunity now to re-start the entire server (including SQL Server).
9 | Turn on SQL Agent and enable jobs.
10 | Turn on Waldoft application consoles except JBOSS_GPRS
=> Check that application is working. Ask application owner to verify no errors on console. => If it is, turn on JBOSS_GPRS and verify new tk_mu_data records on celtrak_data.
11 | Turn on Fozzy, GoSafe, MOTA, System Monitor applications.
=> Check that applications are working. Ask application owner to verify no errors on console.
12 | Generate a full backup on Ernie (do not delete old backup files from Bert).
13 | Enable all Maintenance plans on Ernie.

## Availability Groups
Step | Category | Task | Comment
1 | Enable AlwaysOn | On both servers: Open SQL Server Configuration Manager, SQL Server Services, right click SQL Server (Bert or Ernie), properties, AlwaysOn High Availability, in Windows failover cluster name - select the cluster, then tick box on "Enable AlwaysOn Availability Groups".
Restart each SQL Server after change (obviously don't restart Ernie if you didn't make any change)..
Note: It is necessary to use the same directory in both servers for the database files (ie. E:\data\celtrak_data.mdf, E:\data\ must be a valid directory in both)
2 | Open the port 5022 | If not already done: In both servers: => Run "Windows Firewall with Advanced Security" => Right click "Inbound Rules" and New Rule... => Port => TCP and Specific Local ports: 5022 => Allow the connection => Untick "public" => Name = SQL Server Availability Groups
2b | Open the port 1433 | If not already done: In both servers: => Run "Windows Firewall with Advanced Security" => Right click "Inbound Rules" and New Rule... => Port => TCP and Specific Local ports: 1433 => Allow the connection => Untick "public" => Name = SQL Server Port
3a | Create Logins | Create a SQL Server login [CELTRAK\computer_name$] for each cluster node in each sql server Instance with the appropriate rights. On Ernie USE [master] GO CREATE LOGIN [CELTRAK\ERNIE$] FROM WINDOWS GO On Bert USE [master] GO CREATE LOGIN [CELTRAK\BERT$] FROM WINDOWS GO
3b | Create End Point | Create endpoint for Availability Groups. Execute the following on both Bert & Ernie: => U:\SQL Database Team\Projects\SQL Server 2014 Enterprise Upgrade\Deployment\Create Hadr Endpoint for Availablility Groups.sql
3c | Grant permissions to logins | On Ernie GRANT CONNECT ON ENDPOINT::[Hadr_endpoint] TO [CELTRAK\ERNIE$] GO On Bert GRANT CONNECT ON ENDPOINT::[Hadr_endpoint] TO [CELTRAK\BERT$] GO
4 | Possible Owners of servers within Cluster | Open Powershell, execute the following (Shouldn't be required but do anyway just in case): Get-ClusterResource -Name "Server resounce name (role/resource tab/other resources)" ¦ Set-ClusterOwnerNode -Owners "Node 1 name (ie server name)"; Get-ClusterResource -Name "Server resounce name (role/resource tab/other resources)" ¦ Set-ClusterOwnerNode -Owners "Node 1 name (ie server name)"; IE Get-ClusterResource -Name "SQL Server (BERT)" ¦ Set-ClusterOwnerNode -Owners "ERNIE"; Get-ClusterResource -Name "SQL Server (BERT)" ¦ Set-ClusterOwnerNode -Owners "BERT"; Get-ClusterResource -Name "SQL Server (ERNIE)" ¦ Set-ClusterOwnerNode -Owners "ERNIE"; Get-ClusterResource -Name "SQL Server (ERNIE)" ¦ Set-ClusterOwnerNode -Owners "BERT"; Restart Bert. In Windows Failover Manager, connect to Cluster. Go to Roles. Click on SQL Server (BERT), Resources tab, under other resources, right click on SQL Server (BERT) & properties. In Advanced Policies, you should be both BERT and ERNIE under "possible owners", with only BERT ticked. Repeat check for ERNIE. (If the check for Ernie does not look correct, you may need to restart Ernie, in which case you will need to wait for next outage with to create Availability Group. Try next step regardless).
5 | Create new Availability Group | On Ernie only: => Open SQL Server Management Studio => Connect to the instance, right click AlwaysOn High Availability => New Availability Group Wizard => Availability Group Name = SQL_SERVER_AG => Select all databases => In Replica tab, Add Replaca... and connect to Bert. => Next => In the select synchronous preference section: Choose "Join Only" (Databases on Bert should in NoRecovery state before setting up Availability Groups).
6 | Commit Mode | Right click on SQL_SERVER_AG in mgt studio, and ensure commit mode is "Synchronous".

## Set Ernie to ReadOnly Replica
Step | Category | Task | Comment
1 | Reading material | https://msdn.microsoft.com/en-us/library/hh213002.aspx
http://www.mssqltips.com/sqlservertip/2869/configure-sql-server-2012-alwayson-availability-groups-readonly-routing-using-tsql/
2 | Specify a read_only_routing_url for each node:Bert | /*Execute on Primary Replica (ERNIE)*/
USE MASTER
GO
ALTER AVAILABILITY
GROUP SQL_SERVER_AG
MODIFY REPLICA
ON
'BERT'
WITH
(
SECONDARY_ROLE
(
READ_ONLY_ROUTING_URL='TCP://BERT.celtrak.local:1433'
)
)
3 | Specify a read_only_routing_url for each node:ERNIE | /*Execute on Primary Replica (ERNIE)*/
USE MASTER
GO
ALTER AVAILABILITY
GROUP SQL_SERVER_AG
MODIFY REPLICA
ON
'ERNIE'
WITH
(
SECONDARY_ROLE
(
READ_ONLY_ROUTING_URL='tcp://ERNIE.celtrak.local:1433'
)
)
5 | Set the read routing list from each server to each server: BERt | /*Execute on Primary Replica (ERNIE)*/
USE MASTER
GO
ALTER AVAILABILITY GROUP SQL_SERVER_AG
MODIFY REPLICA ON
'BERT'
WITH
(
PRIMARY_ROLE
(
READ_ONLY_ROUTING_LIST =('ERNIE', 'BERT')
)
)
6 | Set the read routing list from each server to each server: ERNIE | /*Execute on Primary Replica (ERNIE)*/
ALTER AVAILABILITY GROUP SQL_SERVER_AG
MODIFY REPLICA ON
'ERNIE'
WITH
(
PRIMARY_ROLE
(
READ_ONLY_ROUTING_LIST =('BERT','ERNIE')
)
)
7 | Set Ernie as Readable Secondary | On Ernie, in Mgt Studio, go to AlwaysOn High Availability, Availability Groups and right click on SQL_Server_AG (Primary).
Properties, under "Readable Secondary" set Ernie to Yes.
Set Availability mode on both Bert and Ernie to Synchronous (we'll probably change this later).
8 | Validation |  | PS. After executing the above code, all read only requests will go to the secondary server and, in case of failover, will read and write from the primary, even if the application is configured as Read Only
SELECT ag.name as "Availability Group", ar.replica_server_name as "When Primary Replica Is",
rl.routing_priority as "Routing Priority", ar2.replica_server_name as "RO Routed To",
ar.secondary_role_allow_connections_desc, ar2.read_only_routing_url
This is script will help to validate the configuration:
FROM sys.availability_read_only_routing_lists rl
inner join sys.availability_replicas ar on rl.replica_id = ar.replica_id
inner join sys.availability_replicas ar2 on rl.read_only_replica_id = ar2.replica_id
inner join sys.availability_groups ag on ar.group_id = ag.group_id
ORDER BY ag.name, ar.replica_server_name, rl.routing_priority
9 | For information purposes only | /* Manual "Automatic" Failover */ | Use this if you want to try to turn manual failover into an automatic failover.
USE master
GO
WHILE (1=1)
BEGIN
WAITFOR DELAY '00:00:10'
BEGIN TRY
SELECT top 1 ID FROM [BERT].model.dbo.sysobjects
END TRY
BEGIN CATCH
ALTER AVAILABILITY GROUP [SQL_SERVER_AG] FAILOVER;
BREAK
END CATCH
END

## New Node to FCI
Order | Task
1 | Connect to the new server, open Server Manager, add new Features (as previous steps) add .NET Framework 3.5 and Failover Cluster (same as before).
2 | Ask Eoghan to set the cluster disks to be also seen by this server (not sure what is that, but he knows what to do)
3 | Implement SAN changes steps 7-10 only (Refer to "SAN & IT Settings" tab).
4 | Verify server settings (Refer to OS Server Settings tab).
4.1 | Steps 12-15 in SQL Server settings tab.
5 | Open Failover Cluster Manager, connect to SQLCLUSTER, expand, right click "nodes", "add node", type the server name. Follow the steps: => Do validation tests => Under Review storage status: DO NOT SELECT ANY DISKS => Add validation report, in Confirmation section, untick "Add all eligible storage to the cluster".
6 | Check if port 5022 is open on the firewall of this server. If not, add it: => Run "Windows Firewall with Advanced Security" => Right click "Inbound Rules" and New Rule... => Port => TCP and Specific Local ports: 5022 => Allow the connection => Untick "public" => Name = SQL Server Availability Groups
7 | Check if port 1433 is open on the firewall of this server. If not, add it: => Run "Windows Firewall with Advanced Security" => Right click "Inbound Rules" and New Rule... => Port => TCP and Specific Local ports: 1433 => Allow the connection => Untick "public" => Name = SQL Server Port
8 | Run SQL Server 2014 Installation Setup, select "Add node to a SQL Server failover cluster". Follow the steps: => As before, during rule check if you get "Network binding order" warning. Follow same steps as "SQL Installation FCI" tab. => Cluster Node configuration: Change SQL Server Instance to Bert (or Ernie depending on FCI) => Service account: Type in e*.. password 4 times
9 | IF A MESSAGE TO ADD DISK POP UP, NEVER SELECT ANY OF THEM, it may shutdown the AG
10 | Create a SQL Server login [CELTRAK\computer_name$] for each cluster node in each sql server Instance with the appropriate rights: USE [master] GO CREATE LOGIN [CELTRAK\BERT1$] FROM WINDOWS GO GRANT CONNECT ON ENDPOINT::[Hadr_endpoint] TO [CELTRAK\BERT1$] GO
11 | Possible Owners:
In Failover cluster Manager, connect to SQLCLUSTER, in Roles, Resources tab, under Other Resources, go to properties of SQL Server (BERT) and SQL Server (ERNIE).
In Advanced Policies tab, select the appropriate "possible owners" (in Bert role should have both unit 9 servers as possible owners).

## Troubleshooting AG
Issue | Task to resolve
A secondary database is "Not Synchronizing". | On both Primary (SQL_SERVERAG_L) and Secondary server, exec: => ALTER DATABASE database_name SET HADR RESUME Alternatively, Connect to secondary SQL server in Mgt Studio/AlwaysOn High Availablilty/Availability Groups/SQL_Server_AG/Availability Databases/right click database and REsume Data Movement
Secondary replica shows "Not Connected". | If the replica shows the message "Not Connected", probably we have doors closed in the firewall.
Other | Check if the ports 1433, 5022 and the one use by the listener (recomended 1433) are opened in all participants servers
Other | Be sure that you have executed all configuration scripts mentioned on "Availability Groups" tab. The following script help to find out
Bring Cluster back online | PowerShell (From any running server that should be part of Cluster):
(If cluster came down unexpectedly)
1.Use Stop-ClusterNode to make sure that the cluster service is stopped.
Stop-ClusterNode –Name "SQLCLUSTER"
2.Use Start-ClusterNode with –FixQuorum to force the cluster service to start.
Start-ClusterNode –Name "ERNIE" -FixQuorum
3.Use Get-ClusterNode with –Propery NodeWieght = 1 to set the value the guarantees that the node is a voting member of the quorum.
(Get-ClusterNode –Name "ERNIE").NodeWeight = 1
4.Validate Cluster Node Vote
Get-ClusterNode –Name "ERNIE" ¦ Select-Object NodeName, State, NodeWeight