## Pre-Deployment Checklist
This is a list of pre-Deployment taks that should be completed before a "hard" release for celtrak_data database changes..
More detailed note on pre-Deployment tasks can be found in "SQL Release to Live Process Rough Notes.docx".
Order | Task | Completed (Y/N) | Completed Date
1 | Decide if hard or soft release (ensure to reveiw cycle scripts also). | Y | 2016-02-16
2 | Review Currently Editing SQL and cycle scripts. Clean up where required (naming conventions, temporary table instead of table variables, etc). | N
3 | We are not deploying all code in trunk to Live. Document each change that is being made so that nothig get forgotten on the day. | N
4 | Deploy code to a live copy on Dev | N
5 | Optional: If you want (for larger releases), point dev application to Live copy DB on beaker and request a re-test (Ask Kevin to set up a GPRS spray, turn on SQL agent jobs, run all reports, etc) | N
6 | Check if any other non-celtrak_data code needs to be released. If so, itemise it. | N
7 | Document a rollback strategy | N

## Deployment Checklist
Day | Database | Task |  | Status
Day before deployment | Trunk | Review SVN and ensure that no changes have been made to code since the last review.
Day of Deployment | ALL | Stop applications (Waldorf and Fozzy/Comms).
Stop SQL Agent using Failover Cluster Manager.
Run SQL Agent job "Transaction Logs" to back up latest transaction logs. Wait until trn files complete.
Run SQL Agent job "Transaction Logs Celtrak Data Archive" to back up latest archive transaction logs. Wait until trn files complete.
Day of Deployment | ALL | Suspend System Monitor Alerts
Day of Deployment | ALL | Run sp_who2 'Active' to see what connections to SQL Server still exist ("count_active_DB_connections.sql" might be better than sp_who2 here).
| ALL | Suspend Data Movement: => On Primary SQL Server, open Management Studio/AlwaysOn High Availability/Availabilty Groups/SQL_SERVER_AG/Availability Databases Right click on each database and Suspend Data Movement. NB Keep an eye on storage while doing deployment to make sure transaction logs don't get too big.
Day of Deployment | celtrak_data | Time to apply celtrak_data code in svn.
Apply list of SQL changes that has been documented.
Day of Deployment | ALL | Start applications (Waldorf and Fozzy/Comms).
Day of Deployment | ALL | Start SQL Agent.
Day of Deployment | ALL | Monitor SQL Agent Jobs for sucessful execution.
Day of Deployment | ALL | On Primary, review SQL Error Logs for any issues: => Execute "Review all records in SQL Server error log" in SQL tab.
Day of Deployment | ALL | Resume Data Movement: => On Primary SQL Server, open Management Studio/AlwaysOn High Availability/Availabilty Groups/SQL_SERVER_AG/Availability Databases Right click on each database and Resume Data Movement.
Day of Deployment | ALL | On Secondary, review SQL Error Logs for any issues: => Execute "Review all records in SQL Server error log" in SQL tab.
Day of Deployment | ALL | Start Transaction log SQL Agent jobs
Day of Deployment | ALL | Activate System Monitor alerts
Day of Deployment | ALL | Go Home and keep as eye on things.
DB Sync
JMS data queue
Size of the transaction log files and temp files in both servers.
Monday after Release | ALL | Post release items
Add any new tables to "tmp_reference tables" in Trunk.
Monday after Release | celtrak_data |  | Add code to Trunk SVN.
Do a local build from Trunk svn.
Tuesday after Release | ALL |  | Assess sproc duration and performance of new/changed sprocs since deployment
1 week after Release | celtrak_data_tkdemo2 | Do we need to apply any changes to TK Demo or Combo Demo databases on Beaker with new code.

## SQL
/*Start: SQL: Review all records in SQL Server error log (in last hour)*/
/*Execute on both the Primary and Secondary*/
DECLARE @ltbl_sql_server_error_log TABLE (
log_date DATETIME
, process_info VARCHAR(100)
, text VARCHAR(8000)
)
INSERT INTO @ltbl_sql_server_error_log
EXEC sp_readerrorlog 0 --log file you want to read: 0 = Current, 1 = Archive #1, 2 = Archive #2, etc
, Null --log file type. 1 or Null = error log. 2 = SQL Agent log.
, NULL --string one you want to search for.
, NULL --string two you want to search for (to further refine results).
SELECT 'Current SQL Sever Error Log: All in last hour' as description
, *
FROM @ltbl_sql_server_error_log
WHERE process_info <> 'Backup'
AND log_date > DATEADD(hh,-1,getdate())
ORDER BY log_date DESC
/*End: SQL: Review all records in SQL Server error log (in last hour)*/